|  |
| --- |
| **Project Deliverables and Payments Table**(Note: GST AMOUNT and TOTAL PAYMENT columns are optionally completed) |
| **Deliverable or milestone** | **Demonstrating the deliverable is complete** | **Due date** | **Payment amount (excluding GST)** | **GST amount** | **Total payment amount (including GST)** |
| Milestone 1 | Provision of the following to DoT:A tax invoice; andA copy of the signed MOU | 15 December 2019 | $15,000 | $1,500 | $16,500 |
| Milestone 2 | Establish steering committee and terms of reference (include DoT committee member);Appoint Coordinator; Finalise detailed project plan and evaluation plan;Recruit and train volunteers;Submit quote for vehicle; andA tax invoice. | 15 June 2020 | $40,000 | $4,400 | $44,000 |
| Milestone 3 | Evidence of Vehicle Purchase;Evidence that $76,790 has been expended on the project;A report on the future sustainability of the service, to be prepared in consultation with DoT and Commercial Passenger Vehicles Victoria;Project Evaluation Report; and.A tax invoice. | 30 June 2021 | $9,850 | $985 | $10,835 |